## R0 & R1 Features
Feature ID | Feature Name | Release | Sprint | Priority | Status | Detail
FR-001 | Monorepo & Infrastructure Setup | R0 | R0-1 | Critical | Complete | Turborepo monorepo with pnpm workspaces, 4 packages (api, web, db, shared), PostgreSQL 16 via Drizzle ORM with 32 tables
FR-002 | Database Schema & Migrations | R0 | R0-1 | Critical | Complete | 32 table definitions covering projects, tasks, users, AI, integrations. 4 SQL migrations applied including multi-workspace support
FR-003 | JWT Authentication & Login | R0 | R0-2 | Critical | Complete | Email + password + workspace login with JWT access and refresh tokens. Fastify 5 REST API with @fastify/jwt
FR-004 | Multi-Workspace Support | R0 | R0-2 | High | Complete | Global accounts table separate from per-tenant user memberships. Two-step login flow, workspace switcher in sidebar
FR-005 | Role-Based Access Control | R0 | R0-2 | Critical | Complete | Four roles: site_admin, pm, developer, client. Middleware checks on all protected routes
FR-006 | Task CRUD & Workflow | R0 | R0-2 | Critical | Complete | Create, update, delete tasks with status workflow (created, ready, in_progress, review, completed, blocked, cancelled), priority levels, sub-tasks
FR-007 | Project Management | R0 | R0-2 | High | Complete | Project CRUD with status tracking, phases per project, WBS baseline storage, task counts and progress metrics
FR-008 | AI Orchestration Engine | R0 | R0-3 | High | Scaffolded | Database tables for ai_actions, ai_sessions, ai_agent_configs, ai_cost_log. Routes for execute, review, and sessions exist
FR-009 | AI Review & Sessions UI | R0 | R0-4 | Medium | Scaffolded | AI review page with approval/rejection flow and AI sessions page built but hidden from sidebar navigation
FR-010 | Dashboard with Charts | R0 | R0-5 | High | Complete | Dashboard page with Recharts — pie charts for task status and priority, line chart for 14-day activity, stat cards, What's Next section, AI summary
FR-011 | Dependency Management | R0 | R0-5 | High | Complete | Blocker/blocked relationships between tasks with BFS-based circular dependency detection and visual dependency management page
FR-012 | Team Management | R0 | R0-5 | Medium | Complete | User list with roles, invite new users, role management for admin/pm, user deactivation
FR-013 | Comments & Mentions | R0 | R0-5 | Medium | Complete | Task comments with @mention extraction, mention tracking table, comment CRUD operations
FR-014 | Audit Log | R0 | R0-6 | High | Complete | Immutable activity trail for all mutations with human-readable format, entity type filters, search, date range, CSV export, pagination
FR-015 | Notifications Inbox | R1 | R1-1 | High | Complete | In-app notification inbox with unread count, filter by all/unread, mark individual or all as read
FR-016 | Send Notifications to Team | R1 | R1-1 | Medium | Complete | Send in-app notifications to teammates about specific tasks via a form that loads users and tasks on demand
FR-017 | Kanban, Calendar, Table Views | R1 | R1-2 | High | Complete | Three additional view modes for tasks — drag-drop kanban board, calendar view, and spreadsheet-style table view
FR-018 | Timeline View | R1 | R1-2 | Medium | Complete | Gantt-style timeline view added as a tab inside My Tasks alongside list, kanban, calendar, and table views
FR-019 | Saved Views & Recurring Tasks | R1 | R1-3 | Medium | Complete | Saved filter presets for task views. Recurring task schedules with cron expressions, enable/disable, next run tracking
FR-020 | Portfolio Dashboard | R1 | R1-3 | Medium | Complete | Cross-project overview with donut charts (completion, project status), overdue bar chart, color-coded stat cards, clickable project cards